## According to website April 18
No. / Dept | Commitment | Milestone 2012/13 | Milestone 2013/14 | Milestone 2014/15 | Priority | Update on Northern Ireland Executive's website as of April 18, 2016 | Update from department after inquiries from The Detail | Progress report according to the Executive | Progress report according to The Detail | Notes
DETI | Contribute to rising levels of employment by supporting the promotion of over 25,000 new jobs | 13 300 jobs | 19 500 jobs | 25 000 jobs | 1 | PfG Commitment achieved. 37,277 jobs promoted. |  | Achieved | Achieved | The Detail asked DETI how many of these jobs were created as jobs promoted is not the same as creation. The department did not respond.
DFP, OFMDFM, DETI | Press for the devolution of Corporation Tax and reduce its level | Press for a UK government decision, through participation in Joint Ministerial Working Group | Work to ensure that required Westminster and Assembly legislation is in place to give effect to any Executive decisions | Executive announcement of rate of corporation tax for Northern Ireland | 1 | The Corporation Tax (Northern Ireland) Act enables the devolution of Corporation Tax from April 2017. |  |  | Partially achieved | Legislation doesn't come into effect until April 2017 so corporation tax level still in line with the rest of the UK. It could potentially see corporation tax reduced to 12.5% as in the Republic of Ireland, but the delivery of this commitment remains unclear.
DETI | Achieve £1 billion of investment in the Northern Ireland economy | Secure total investment of £550.0m | Secure total investment of £320.5m | Secure total investment of at least £1 billion. | 1 | PfG Commitment achieved. £2.672 billion invested |  | Achieved | Achieved
DETI | Increase the value of manufacturing exports by 20% | Increase by 6 percentage points | Increase by 7 percentage points | Increase by 7 percentage points | 1 | 6.7% growth on the baseline year (2010/11 financial year) achieved. |  | Not achieved | Not achieved | According to the update provided by DETI, it has failed to reach its target.
DETI | Support £300 million investment by businesses in R&D, with at least 20% coming from Small and Medium sized Enterprises | Support £150m investment | Support £75m investment | Support £75m investment | 1 | PfG Commitment achieved. £520 million supported, 27% from SMEs. |  | Achieved | Achieved
DETI | Increase visitor numbers to 4.2 million and tourist revenue to £676 million by 2014 | Increase tourism revenue to £591m and tourism visitor numbers to 3.47m | Increase tourism revenue to £625m and tourism visitor numbers to 3.6m | Increase tourism revenue to £676m and tourism visitor numbers to 4.2m | 1 | PfG Commitment achieved. 4.5 million visitors, £751 million revenue in 2014. |  | Achieved | Achieved | But over half (52%) of the visits made in 2014 were made by local residents. (See: https://www.detini.gov.uk/sites/default/files/publications/deti/2014-Annual-publication.pdf)
DETI | Aid liquidity of Small and Medium Size Enterprises (SMEs) through a £50 million loan fund | Support 50 SMEs by providing loans valued at £8m | Support 50 SMEs by providing loans valued at £10m | Support 50 SMEs by providing loans valued at £10m | 1 | PfG Commitment achieved. £31 million loans issued against cumulative target of £28 million. |  | Achieved | Achieved | Even though £50million was said to be available, the target was £28 million over three years (http://www.northernireland.gov.uk/pfg-2011-2015-final-report.pdf)
DOE | Ensure 90% of large scale investment planning decisions are made within 6 months and applications with job creation potential are given additional weight | 60% | 75% | 90% | 1 | 2012/13 performance – 72% against 60% target; 2013/14 performance – 92% against 75% target; 2014/15 performance – 68% against 90% target. During 2014/15 the preparation for the transfer of the majority of planning functions to the new council structures on 1 April 2015 impacted on the Department’s ability to meet this commitment. |  | Not achieved | Not achieved | The target was met during first two years, as mentioned in the update, but not in the third year.
DFP | Introduce extension of Small Business Rate Relief Scheme to 2015 | Ensure legislative and operational changes will be effective |  | Review operation of scheme | 1 | PfG Commitment achieved. |  | Achieved | Achieved
DFP | Hold the Regional Rate increases to the rate of inflation | Secure approval to Rates Order | Secure approval to Rates Order | Secure approval to Rates Order | 1 | PfG Commitment achieved. |  | Achieved | Achieved
DFP | Eliminate Air Passenger duty on direct long haul flights | Agree policy etc | Ensure progress of Assembly Bill etc |  | 1 | PfG Commitment achieved. |  | Achieved | Achieved
DSD | Invest in social enterprise growth to increase sustainability in the broad community sector | Develop and implement policy | Baseline existing social enterprise activity etc | Commence implementation etc | 1 | PfG Commitment achieved. The policy framework for Community Asset Transfer has been published and is being implemented by a cross departmental oversight group. |  | Achieved | Unclear | The Detail asked DSD what the investment referenced in the commitment looked like (i.e. if it was a financial investment or policy creation). The department did not respond.
DETI | Encourage achievement of 20% of electricity consumption from renewable sources by 2015, Encourage 4% renewable heat by 2012 | 12% Electric, 2% Renewable Heat | 15% electricity, 3% Renewable Heat | 20% electricity, 4% Renewable Heat | 1 | PfG Commitment achieved. The figure for renewable generation for the year ending March 2015 is 20%. An estimated 3.1% of total heat consumption comes from renewable technologies. |  | Achieved | Partially achieved | While renewable generation is 20%, the figure for renewable heat target appears not to have been met.
DCAL | Support 200 projects through the Creative Industries Innovation Fund | 100 projects | 150 projects | 200 projects | 1 | PfG Commitment achieved. The Arts Council made a total of 203 awards through the Creative Industries Innovation Fund. |  | Achieved | Achieved
OFMDFM | Develop Maze/Long Kesh as a regeneration site of regional significance | Launch of Development Plan etc | Balmoral Show Commencement of site infrastructure works etc | Private sector development partner appointed Peace building and Conflict Resolution Centre complete | 1 | There is no current agreement on Maze/Long Kesh issues. Ministers continue to discuss a way forward. |  | Not achieved | Not achieved
OFMDFM | Develop the 'One Plan' for the regeneration of Derry/Londonderry, incorporating the key sites at Fort George and Ebrington | 1175 jobs promoted etc | 1670 jobs promoted etc | 1200 jobs promoted etc £23m infrastructure investment programme | 1 | PfG Commitment achieved. Jobs promotion targets for 2012/13 and 2013/14 having been met and exceeded. 861 jobs were promoted in the year to 31 March 2015. In addition to the jobs promoted, a further 35 high value research and development posts were created at Seagate and 113 jobs in the former Derry City Council area were safeguarded. The North West Science Park and capital developments at Ebrington will be opportunities for further job creation, and the site at Ebrington will continue to be promoted to maximise employment opportunities. |  | Achieved | Unclear | One Plan says it is a strategic regeneration plan for Derry~Londonderry which sets out a vision of delivering 12,900 jobs by 2020. However, an independent report from July 2015 into Ilex (which was the lead body for eight programmes in the One Plan) was critical of its progress. It found it did not deliver 'on the Programme for Government target of completing £23m infrastructure investment at Ebrington by March 31, 2015, and no private sector jobs have been created on the site'. (https://www.ofmdfmni.gov.uk/sites/default/files/publications/ofmdfm/ilex-review-final-appendices-report-july-2015.pdf)
OFMDFM | Provide financial and other support across government to ensure the success of the Derry/Londonderry City of Culture 2013 | Creative industries hub in place | Visitor numbers to the City and visitor spend doubled | City of Culture programme supported and delivered | 1 | PfG Commitment achieved. |  | Achieved | Achieved
DETI | Provide financial and other support across government to ensure the success of the Our Time Our Place Initiative in 2012 including marking the centenary of Titanic’s Maiden Voyage | Support the 2012 events | Achieve legacy benefits etc | Achieve legacy benefits etc | 1 | PfG Commitment achieved. Events hosted include: the Titanic Festival, Clipper Maritime Festival, opening of the Giant's Causeway Visitor Centre, the 2012 and 2015 Irish Opens, the 50th Belfast Festival at Queens, the City of Culture Celebrations, the G8 Summit, and the Giro D'Italia Grande Partenza. |  | Achieved | Achieved | The NI Tourist Board spent £11.2million on the Our Time Our Place advertising campaign in 2012.
DRD | Progress the upgrade of key road projects and improve the overall road network to ensure that by March 2015 journey times on key transport corridors reduce by 2.5% - against the 2003 baseline | Improve the strategic road network etc | Improve the strategic road network etc | 2.5% reduction in journey times | 1 | This PfG period saw the results of a commitment to reduce journey times on the Strategic Road Network, which reflects the implementation of the Strategic Road Improvement Programme (SRIP) over a 12 year period. The 2013 survey results indicated an increase in journey times over the 2003 baseline. A further survey, completed in November 2014, confirms an increase in journey times of 3.14% over the 2003 baseline. Implementation of the SRIP continues. For example the A8 Belfast – Larne dual carriageway is expected to open to traffic in summer 2015 and construction of the A26 Glarryford to A44 dualling has commenced. |  | Not achieved | Not achieved | Journey times have increased over the 2003 baseline.
DEL | Increase uptake in economically relevant Science, Technology, Engineering and Mathematics (STEM) places | 233 additional places | 467 additional places | 700 additional places | 1 | PfG Commitment achieved. Funding for the additional 233 places in 2014-15 (cumulative total 700) has been put in place and the universities and colleges notified of this in advance of the 2014-15 academic year. |  | Achieved | Achieved | The milestones look to have been achieved between 2009/2010 and 2013/2014 when there was a 1,505 increase in number of students enrolled in 'narrow' STEM subjects and 280 increase in 'broad' STEM subjects at higher education institutions in Northern Ireland. Latest statistics show an increase in the proportion of NI higher education students doing these subjects [narrow: 23.9% in 2013/14 to 24.8% in 2014/15 / broad: 45.3% to 46.2% ]. However, the two universities both announced plans to cut undergraduate places last year amid planned Government funding cuts.
DE | Increase the overall proportion of young people who achieve at least 5 GCSEs at A* - C or equivalent including GCSEs in Maths and English by the time they leave school. Including increasing the proportion of young people from disadvantaged backgrounds who achieve at least 5 GCSEs at A* - C or equivalent including GCSEs in Maths and English. | 61% (42%) | 63% (45%) | 66% (49%) | 1 | The milestone target in respect of the commitment to increase the overall proportion of school leavers achieving at least 5 GCSEs A*-C (or equivalent) including GCSEs in English and Maths has been achieved. Although proportion of school leavers with FSME falls short of the milestone there has been an increase in the proportion achieving this measure. The percentage of school leavers who have met the required standard was 59.5% in 2010/11, 62.0% in 2011/12, 62.2% in 2012/13, and 63.5% in 2013/14. The proportion of school leavers entitled to free school meals achieving this measure was 31.7% in 2010/11, 34.1% in 2011/12, 34.9% in 2012/13 and 34.9% in 2013/14. |  |  | Partially achieved | While there has been an increase in the overall proportion of school leavers achieving 5 GCSEs (indicator 1), the annual targets for school leavers entitled to free school meals (indicator 2) have not been met. See here for more information on commitment pledges: http://www.northernireland.gov.uk/pfg-delivery-plans-commitment-21-and-42.pdf
DHSSPS | Allocate an increasing percentage of the overall health budget to public health | Strengthen the drive on improving health and mental wellbeing and reducing health inequalities etc | The HSC will have in place, all the arrangements necessary to extend bowel cancer screening etc | Invest an additional £10m in public health | 1 | PfG Commitment achieved. The new Public Health Strategic Framework - Making Life Better - was published on 24 June 2014 and implementation has commenced. Investment in key areas in 2014/15 included: Service improvements to support Diabetic Retinopathy; Breast screening; Cervical screening; Promotion of screening uptake including full roll out of the Bowel screening programme; Extension of sexual health services; Development of the Organ Donation Campaign; and Additional support for vulnerable groups. |  | Achieved | Achieved | The Detail asked DHSSPS to confirm if an additional £10m was invested in public health as per the 2014/15 milestone. The department did not respond.
DARD | Eradicate brucellosis in cattle by March 2014 | 0.03% | 0% | 0% | 1 | PfG Commitment achieved. Excellent progress is being made towards achievement of Official Brucellosis Free Status as a result of DARD and Industry efforts. The annual confirmed herd incidence reached zero (0.00%) on 28 February 2013, one year ahead of target. The last case of confirmed infection was in February 2012. |  | Achieved | Achieved | Northern Ireland was awarded Officially Brucellosis Free (OBF) status on October 6, 2015, with effect from February 1, 2016.
DARD/DETI | Develop a strategic plan for the Agri-food sector | New Food Strategy Board in place etc | Strategic vision implemented etc | Strategic vision implemented etc | 1 | PfG Commitment achieved. The Agri-Food Strategy Board published Going for Growth in 2013 and the Executive's response was published in 2014. Implementation is ongoing and good progress is being made across a broad range of areas, including proposals to introduce a major Farm Business Improvement Scheme, creation of an industry-led agri-food marketing body and targeting of key export markets. |  | Achieved | Achieved
DEL | Upskill the working age population by delivering over 200,000 qualifications | 105,000 qualifications | 53,000 qualifications | 53,000 qualifications | 1 | PfG Commitment achieved. In 2011/12, 66,124 qualifications were obtained; in 2012/13, 73,332; in 2013/14, 78,844; in 2014/15, 80,450. The total for the PfG period is therefore 298,750, against a target of 200,000. |  | Achieved | Achieved
OFMDFM | Facilitate delivery of the Executive's 20% target for increased drawdown of competitive EU funds | Establish baseline etc | Effective drawdown | 20% achieved | 1 | PfG Commitment achieved. In the baseline year (2010/11) the Executive drew down £13.4 million. In 2011/12, £23 million was drawn down. In 2012/13, £18.3 million was drawn down. In 2013/14, £31.3 million was drawn down. |  | Achieved | Achieved
DEL/DETI | Develop and implement a Strategy to reduce economic inactivity through skills, training, incentives and job creation | Develop Strategy | Implement key actions | Further implementation of key actions | 1 | PfG Commitment achieved. Following a successful and extensive public consultation process and subsequent development work, a strategy to tackle economic inactivity has been published and the implementation of a number of key actions has commenced. |  | Achieved | Achieved
DSD | Deliver 8,000 social and affordable homes | 1,325 social and 500 affordable homes delivered | 1,275 social and 500 affordable homes delivered | 2,000 social and 500 affordable homes delivered | 2 | PfG Commitment achieved. 6,101 social homes and 3,963 affordable homes have been delivered in the PfG period. |  | Achieved | Achieved | However, experts have said housing need is much greater than the 8,000 target, while it is claimed that government figures are not sufficiently transparent.
DSD | Introduce and support a range of initiatives aimed at reducing fuel poverty across Northern Ireland including preventative interventions | 9,000 homes improved | 9,000 homes improved | 9,000 homes improved | 2 | PfG Commitment Achieved. Through Affordable Warmth, the Boiler Replacement Scheme, and Warm Homes, 15,972 improvements have been made to homes to help tackle fuel poverty. |  | Achieved | Unclear | Measures have been introduced but fuel poverty has not been reduced. According to the latest stats available (from 2011), 42% of households were in fuel poverty with charity Age Sector Platform accusing Northern Ireland of being the worst region in the UK at tackling the problem. This is one of the highest rates in Western Europe, according to the Consumer Council. Concerns were raised in the House of Commons in December 2015 over the fact pensioners in Northern Ireland are exempt from the UK Government's Warm Homes Discount Scheme. The Detail asked the department how much funding the Warm Home Scheme receives and if it can provide evidence to show that fuel poverty has reduced in Northern Ireland. The department did not respond.
DSD | Improve thermal efficiency of Housing Executive stock and ensure full double glazing in its properties | Implement Programme from 1 April 2012 | 50% completed by March 2014 | Full completion by March 2015 | 2 | All schemes started, however, due to the performance of one contractor, a number were not completed by March 2015. Work has been reallocated to ensure the delivery of the Programme for Government commitment to ensure full double glazing in NIHE properties. |  | Not achieved | Not achieved
OFMDFM | Provide £40 million to address dereliction and promote investment in the physical regeneration of deprived areas through the Social Investment Fund (SIF) | Produce Strategic Action Plans etc | All key milestones for physical regeneration met | To have achieved agreed milestones and completed an evaluation of expenditure | 2 | At 31 March 2015, £19.7 million has been committed to SIF capital projects. This represents 49% of the original budget. |  | Not achieved | Not achieved
OFMDFM | Invest £40 million to improve pathways to employment, tackle systemic issues linked to deprivation and increase community services through the Social Investment Fund (SIF) | Produce Strategic Action Plans etc | Demonstrated improvements on all short term or lead measures | Demonstrated positive trends on lead measures etc | 2 | At 31 March 2015, £30.9 million has been committed to SIF revenue projects. This represents 77% of the total budget. |  | Not achieved | Not achieved
OFMDFM | Publish and implement a Childcare Strategy with key actions to provide integrated and affordable childcare | Develop and begin to implement strategy etc | Achieve at least £3 million of expenditure etc | Achieve remaining expenditure and the key milestones etc | 2 | PfG Commitment achieved. The Childcare Strategy was launched in September 2013 and included 15 Key First Actions to address identified needs and priorities. All of the Key First Actions were underway by the end of March 2014 including the School Age Childcare Grant Scheme which was launched on 27 March 2014. The first call for applications resulted in 50 successful schemes worth £1.9m over a three year period and will create or sustain 1,500 places. Letters of offer were issued in December 2014. A second call for applications closed on 30 September 2014 and resulted in 33 successful schemes worth £1.1m over a three year period, which will create or sustain around 800 places. Letters of offer were issued in April 2014. |  | Achieved | Not achieved | A draft childcare strategy, proposing 22 actions, was put out to consultation last year and closed in November. The final version does not appear to have been published yet. Charity Employers for Childcare, which lobbies for 'family friendly policies in the workplace', claims the executive is still to launch a full childcare strategy and that most of the £12m allocated to the initiative has not been spent. The Detail asked OFMDFM to respond to this claim but the department did not answer our request. For latest on this, see here: https://www.ofmdfmni.gov.uk/articles/childcare-strategy
OFMDFM | Deliver a range of measures to tackle poverty and social exclusion through the Delivering Social Change delivery framework | Establish and begin to implement the Delivering Social Change framework etc | Implement key milestones across all of the projects etc | Evaluate performance etc | 2 | PfG Commitment achieved. The range of measures delivered under Delivering Social Change include: 232.3 full time equivalent teachers appointed under the literacy and numeracy programme; 20 new Nurture Units supporting 256 children 2,635 families referred to existing and new Family Support Hubs; some 1200 families benefitting from the implementation of the Support for Parents programme; eleven Social Enterprise Incubation Hubs have been established; 720 families have completed the Community Family Support Programme. A Play and Leisure Programme is in development. |  | Achieved | Achieved | The Detail asked the department if the performances have been evaluated as per the 2014/2015 milestone. It did not respond.
OFMDFM | Use the Social Protection Fund to help individuals and families facing hardship due to the current economic downturn | Develop proposals etc | Implement longer term programmes etc | Implement longer term programmes etc | 2 | PfG Commitment achieved. It has now been agreed to subsume the Social Protection Fund into one consolidated and integrated ‘Delivering Social Change Fund’ This Fund affords Ministers the opportunity to quickly respond in a flexible manner to urgent social needs as they arise and address the specific needs of some of our most in need individuals and families. |  | Achieved | Unclear | Set up in 2011, a budget of £20 million was identified for the Social Protection Fund in its first year when ministers decided a Winter Poverty Payment should be a priority for the initiative and all the money would be used for that. However, no figures have been provided to show how many families received this payment and if the full amount was spent. The Detail asked OFMDFM how many families have been helped as a result of this fund and if the total £20million allocated to it in 2011 was spent. We also asked if the value of the fund remained at £20 million each year throughout the duration of the Programme for Government but did not receive a response.
DEL | Support people (with an emphasis on young people) in to employment by providing skills and training | 65000 | s | 114,000 cumulative | 2 | PfG Commitment achieved. In total, 37,970 people were supported into work in 2011/12, 38,871 in 2012/13, 38,312 in 2013/14, and 35,946 by March 15. Total 151,099. | This PfG Commitment has been achieved. The figures include the Job Seekers Allowance into employment figures and the Return to Work Credit recipients in the Lone Parent and Employment and Support Allowance (ESA) client groups. | Achieved | Achieved | The department failed to provide a breakdown of how the figures correspond to the various government programmes used to meet the PfG target, or to identify how government met the commitment to target young people.
OFMDFM | Fulfil our commitments under the Child Poverty Act to reduce child poverty | Develop an action plan etc | Implement key milestones and monitor performance etc | Evaluate performance etc | 2 | The Child Poverty Annual Report 2013-14 was agreed by the Executive on 26 February and laid in the Assembly on 2 March. The Child Poverty Strategy will be agreed by the Executive and laid in the Assembly as soon as possible. |  | Not achieved | Not achieved | The Child Poverty Act imposes a legal duty on Governments to aim for levels of less than 10% for relative child poverty and less than 5% in absolute child poverty by 2020. According to the OFMDFM website, approximately 101,000 (23%) children live in relative income poverty. Research by the Institue of Fiscal Studies, published in November 2014, suggests child poverty will rise by 2020.
OFMDFM | Extend age discrimination legislation to the provision of goods, facilities and services | Develop and consult on proposals etc | Progress legislation | Complete legislation | 2 | In February 2015, the First Minister and deputy First Minister announced their decision to bring forward proposals to prohibit unfair age discrimination against people aged 16 and over by those providing goods, facilities and services. On 1 July 2015, the First Minister and deputy First Minister launched a consultation on policy proposals to extend age discrimination to the provision of goods, facilities and services. When OFMDFM has concluded its policy consideration, and agreed a robust policy position, the First Minister and deputy First Minister will then consider all the options available to them for bringing this legislation before the Assembly. |  | Not achieved | Not achieved
DRD | For households, ensure no additional water charges during this Programme for Government | Pay annual customer subsidy to NIW | Pay annual customer subsidy to NIW | Pay annual customer subsidy to NIW | 2 | PfG Commitment achieved. As a result of the payment of the consumer subsidy to NI Water, there have been no additional water charges for households during the period. |  | Achieved | Achieved
DEL | Ensure there are no increases in student fees beyond the rate of inflation for Northern Ireland students studying here | Apply policy | Apply policy | Apply policy | 2 | PfG Commitment achieved. There has been no increase in student fees in the Programme for Government period. |  | Achieved | Achieved | Student fees in Northern Ireland could rise to £9,000 if one new funding option suggested by the employment and learning minister is adopted.
OFMDFM | Establish an advisory group to assist Ministers in alleviating hardship including any implications of the UK Government’s Welfare Reform Programme | Establish advisory group and provide report |  |  | 2 | PfG Commitment achieved. |  | Achieved | Achieved
DE | Improve literacy and numeracy levels among all school leavers, with additional support targeted at underachieving pupils | Develop proposals to significantly improve literacy levels etc | Implement and monitor programme | Implement and monitor programme | 2 | PfG Commitment Achieved. The proportion of school leavers achieving GCSE A*-C in English has increased from 69.1% in 2010/11 to 72.6% in 2013/14. The proportion achieving these grades in maths has increased from 65.4% in 2010/11 to 70.2 % in 2013/14. The equivalent figures for school leavers entitled to free school meals are 44% to 47.3% in English and 37.6% to 43.3% in maths over the same period. |  | Achieved | Partially achieved | According to the DE's website, in 2014/15, 67% of year 12 pupils achieved 5 or more GCSEs at grades A*-C (or equivalent) including GCSE English and GCSE maths, an increase from 65.2% in 2013/14. The department's target for this indicator was 66% and 63% respectively. The proportion of free school meal entitled year 12 pupils achieving 5 or more GCSEs at grades A*-C (or equivalent), including GCSE English and GCSE maths, increased from 38.7% in 2013/14 to 45.6% in 2014/15. DE's targets for this indicator were 45% and 49% respectively. Therefore, although the overall commitment has been met, the annual milestones have not. Full commitment text can be found here: http://www.northernireland.gov.uk/pfg-delivery-plans-commitment-21-and-42.pdf
DE | Ensure that at least one year of pre-school education is available to every family that wants it | Identify reasons why parents do not avail of places. Commence implementation of the Review of Pre-school Admissions etc | Based on findings, implement changes to encourage parents to take up places. Continue to implement review of pre-school admissions. | Review progress and take further actions as necessary | 2 | PfG Commitment achieved. 99.9% of children obtained a funded pre-school place (whose parents engaged with the process to the end). | Due to the non-compulsory nature of pre-school education, parents are only offered funded pre-school places‎ in settings for which they have expressed a preference. - the programme for government target is measured at the end of the admissions process. - at the end of the admissions process, 0.1% children had not yet been offered a place in a setting that their parents had expressed a preference for - however ‎places remained available in all Regions at end of the admissions process, and children continued to be placed in funded pre-school places for which their parents had expressed a preference after the end of the admissions process. | Achieved | Achieved | Places have not yet been offered to 0.1 % of children in a setting their parents had expressed a preference for. The Detail asked how many children were affected by the 0.1% gap each year. The department said that the figure referred to 39 children in the year 2015-16.
DHSSPS | Enrol people who have a long-term (chronic) condition, and who want to be enrolled, in a dedicated chronic condition management programme | Identify and evaluate the current baseline etc | Health and Social Care Board / Public Health Agency work with key stakeholders etc | People with a long term condition will be offered access to appropriate programmes | 2 | PfG Commitment achieved. In 2013/14, there were 12,741 participants on structured patient education/self management programmes, a 10% increase on 2012/13. During 2012/13, there were 11,531 participants, a 13% increase on the number of participants in the baseline monitoring year 2011/12. In terms of programme frequency, in 2013/14 there were 841 patient education programmes a 7% increase on 2012/13. A total of 784 patient education/self management programmes were provided in 2012/13, an increase of 25% on the number in 2011/12. Under remote telemonitoring arrangements, in April 2014 to January 2015, there were 413,584 Monitored Patient Days provided for people with a primary diagnosis of heart disease, COPD, diabetes and asthma. |  | Achieved | Achieved
DHSSPS | Invest £7.2 million in programmes to tackle obesity | Invest £2 million in tackling obesity etc | Invest £2.4 million etc | Invest £2.8 million etc | 2 | PfG Commitment achieved. A cross-Departmental Obesity Prevention Steering Group oversees and monitors Departmental actions committed to in the obesity Framework. The Public Health Agency (PHA) leads a multi-agency implementation group to take forward non-Departmental actions. The PHA investment plan for 2014/15 ensured that £2.8m was spent on tackling obesity. A range of regional and local initiatives are underway including: further development of the Active Travel in Schools and the Food in Schools programmes; research to study physical activity in post-primary schools; dietetic support to health improvement programmes; workplace based weight management initiatives; breastfeeding peer support link worker; and investment in outdoor gyms. |  | Achieved | Unclear | The Detail asked DHSSPS to confirm what the total spend was over the period, as only the 2014/2015 figure has been provided. The department did not respond.
DARD | Bring forward a £13 million package to tackle rural poverty and social and economic isolation in the next three years | Finalisation of programme etc. Spend of £4 million | Implementation of programmes. Spend of £4 million. | Implementation of programmes. Spend of £5 million. | 2 | PfG Commitment achieved. 100% of budget spent in each year, and £13.9 million invested over the PfG period. This represents a real benefit to rural communities through funding a broad range of initiatives. |  | Achieved | Achieved
DARD | Advance the relocation of the Headquarters of the Department of Agriculture and Rural Development to a rural area by 2015 | Carry out the necessary appraisal etc | Implement programme for securing appropriate accommodation | Continue to implement programme | 2 | PfG Commitment achieved. Trade Union and staff consultation is ongoing. An Integrated Consultant Team (ICT) have been appointed by Central Procurement Directorate to manage the Ballykelly project up to construction stage taking forward issues such as building design brief, development of access road, planning approvals etc. |  | Achieved | Achieved | A £12m contract to build new DARD headquarters was awarded to J H Turkington and Sons in March 2016. Fisheries have already relocated to Downpatrick and the Forest Service has moved to Inishkeen House, Enniskillen. The Rivers Agency is expected to move to Loughry College, Cookstown, later in 2016.
DETI | Develop and implement a Financial Capability Strategy for consumers | Develop Strategy | Implement key actions | Further implement key actions etc | 2 | PfG Commitment achieved. A report has been produced on the impacts of the Strategy to date, and work continues on the implementation of key actions to support the Strategy. |  | Achieved | Achieved | The department states that work continues on the implementation of key actions to support the strategy. This does not necessarily mean it has been fully implemented.
DOE | Implement a levy on single use carrier bags by 2013 and extend this to reusable bags from April 1 2014 | Operational arrangements/ Subordinate legislation by 31 Jan 2013 etc | Primary legislation and amended subordinate legislation etc | Implement levy | 3 | PfG Commitment achieved. Phase 1 of the levy was introduced with effect from 8 April 2013. Phase 2 of the Levy was introduced on 19 January 2015. |  | Achieved | Achieved
DOE | Continue to work towards a reduction in greenhouse gas emissions by at least 35% on 1990 levels by 2025 | To continue to project at least a 35% reduction etc | To continue to project at least a 35% reduction etc | To continue to project at least a 35% reduction etc | 3 | PfG Commitment achieved. The latest greenhouse gas emission figures, published 9 June 2015, show a 16% drop in greenhouse gas emissions from 1990 to 2013. The current projection is for a 33.3% reduction in GHG emissions against the 35% target by 2025 up from 27.6% in 2011. | The PfG emissions reduction target relates to 2025. The latest greenhouse gas emission figures, published 9 June 2015, show a 16% drop in greenhouse gas emissions from 1990 to 2013. Progress continues to made and the current projection is for a 34.1% reduction (excluding LULUCF) in GHG emissions against the 35% target by 2025, up from 27.6% in 2011. It is therefore too early to say that the target has not been met. | Achieved | Not achieved | Projected target of 35% not met and, while the department says it has achieved the target, it later stated it was "too early" to give a definitive picture.
DOE | Work towards halting the loss of biodiversity by 2020 | Declare 15 additional Areas of Special Scientific Interest etc | Designate a further 15 Areas of Special Scientific Interest etc | Designate an additional 15 Areas of Special Scientific Interest etc | 3 | PfG Commitment achieved. During the PfG period: 40 ASSIs have been designated; an invasive species strategy and a revised biodiversity strategy have been adopted; updated conservation regulations have been made; and, a statutory management scheme for Rathlin Island has been established. | The main focus of the biodiversity PfG is to work towards halting the loss of biodiversity across Northern Ireland. This was supported in 2014/15 by the designation of 10 ASSIs, alongside confirmation of three very significant ASSIs in the Mournes area (in October 2014). These ASSIs were selected for their very wide and complex assemblages of special features including; flora, fauna, geological, physiographical. Due to the large (The Western Mournes ASSI alone was the third largest ever designated in Northern Ireland, at 4740ha) amount of land, number of complex special features requiring survey/recording and number of landowners requiring engagement/liaison to complete the designation process during the 2014/15 reporting period, the Department therefore made substantial progress in the identification and protection of biodiversity across Northern Ireland without meeting the 15 ASSI per year milestone. The ASSI designation programme only forms a part of the whole suite of approaches that the Department uses to work towards halting biodiversity. The development of environment policy to protect the environment, the provision of funding and grants to eNGOs to protect the environment are just two examples of other measures the Department utilises to meet its Biodiversity PfG target. | Achieved | Partially achieved | PfG states that 45 ASSIs should be designated. There are only 40 according to latest DOE update.
DOE | Achieve a household waste recycling or composting rate of 45% by end of March 2015 | Recycling rates of 41% for household waste | Recycling rates of 43% for household waste | Recycling rates of 45% for household waste | 3 | The DOE estimates outturn for 2014/15 of around 42%. | The household waste recycling rate for 2014/15 was 42%. | Not achieved | Not achieved
DOJ | Substantially complete the construction of the new Police, Prison and Fire Training College | Award construction contract | At least 25% of the Programme Capital Budget will be utilised | At least 70% of the Programme Capital Budget will be utilised | 3 | Based on Ministerial responses to the draft Executive Paper circulated on 19 March, the joint Chairs of the Northern Ireland Community Safety College Steering Group wrote to the Chair of the Programme Board in early June, asking that work to develop a revised business case and range of options for the future delivery of Service training be accelerated to enable further briefing to be provided to the Executive after the summer recess. | A revised business case (OBC1) was developed during the 2015/16 year. It was approved by the Executive in March 2016, allowing the Programme Team to proceed with the development of the preferred option to OBC2 stage. OBC2, if approved, will form the basis for DFP approval to initiate formal procurement. The Budget 2016-17 statement, agreed by the Executive in December 2015, made a commitment to provide capital funding for this project over the next five financial years. | Not achieved | Not achieved
DOJ | Reduce the level of serious crime | Publish final cross-departmental Strategic Framework on Reducing Offending etc | Implement 90% of agreed Youth Justice Review recommendations etc | Deliver joined up oversight, evaluation and publication of reducing offending interventions etc | 3 | The Domestic and Sexual Violence strategy is nearing completion. This has included the drafting of an additional one year action plan designed to generate momentum and assist with the initial implementation of the strategy. However, development has been delayed by a number of issues including the need to take account of the current financial situation and to explore, with the voluntary and community sector, how such a strategy might be delivered within reduced resources. To date the Department has provided two written briefings to the Justice Committee on the joined up oversight and evaluation of Reducing Offending interventions. The report reflects the work taken forward since the publication of the Strategic Framework for Reducing Offending in May 2013. The latest report was considered by the Justice Committee on 23 April 2015. Separately, the Department has been developing the use of a Northern Ireland Data Lab Facility to assist in the evaluation of reducing offending interventions; a briefing paper and initial analysis have been published on the DOJ Website. | ‘Supporting Change’, a desistance strategy and action plan to improve outcomes for people who have offended, was published on 28 September 2015. Formal briefing was provided to the Justice Committee on the joined up oversight and evaluation of Reducing Offending interventions. Statistical reports on first time entrants to the justice system (2013/14) and one year proven reoffending rates (2012/13) have also been produced. The joint DHSSPS and DOJ led Stopping Domestic and Sexual Violence and Abuse Strategy was published 15 March 2016.A consultation on an offence of domestic abuse and the introduction of a domestic violence disclosure scheme launched on 5 February 2016 and will close on 29 April 2016. | Achieved | Not achieved | Crime increased by 2.3% between 2013/14 and 2014/15 when there were 102,746 and 105,072 crimes recorded by the PSNI respectively. During the same timeframe, there was a 5.7% increase in offences of violence against the person, sexual offences increased by 22.4%, drug offences were up by 6.7%, possession of weapons offences were up by 6.2%, miscellaneous crimes against society rose by 14.6% and offences of other fraud increased by 3.7%. Reductions were seen in robberies (-8.1%), theft (-1.6%), criminal damage (-0.3%) and public order offences (-5.8%). Incidents with a domestic abuse motivation increased by 2.4% from 2013/14 to 28,287 offences in 2014/15. (While the department failed to provide crime statistics, see police figures here: https://www.psni.police.uk/globalassets/inside-the-psni/our-statistics/psni_statistical_press_release_2014_15_final.pdf)
DOJ | Tackle crime against older and vulnerable people by more effective and appropriate sentences and other measures | Consult Lord Chief Justice on inclusion of older and vulnerable people in sentencing guidelines initiative | Any necessary legislative changes taken forward etc | Implement programme of measures | 3 | PfG Commitment achieved. The action plan for tackling crime against older and vulnerable people is being implemented. Performance indicators for tackling fear of crime among older and vulnerable people in the context of the Community Safety Strategy have been developed by the multi-agency Older Persons Delivery Group and are monitored at each Delivery Group meeting. An annual progress report is submitted to the Justice Committee with the most recent report submitted in April 2015. The age and vulnerability of the victim are included as aggravating factors in the principles underlying sentencing. Measures for transparency, consistency and understanding of sentencing practice were announced by the Minister of Justice in June 2012, and include increased engagement with the Lord Chief Justice (LCJ) and lay membership on the Sentencing Group, established by the LCJ to enhance the guidance available to the judiciary. Professor Sally Wheeler, School of Law, Queen’s University Belfast, has been appointed to the Group. | The action plan for tackling crime against older and vulnerable people is being implemented and annual progress reports are submitted to the Justice Committee, with the most recent report submitted in March 2016. The age and vulnerability of the victim are included as aggravating factors in the principles underlying sentencing. Measures for transparency, consistency and understanding of sentencing practice were announced by the Minister of Justice in June 2012, and include increased engagement with the Lord Chief Justice (LCJ) and lay membership on the Sentencing Group, established by the LCJ to enhance the guidance available to the judiciary. Professor Sally Wheeler, School of Law, Queen's University Belfast, has been appointed to the Group. Since 2010, new guidance has regularly been made available to the judiciary in the form of sentencing guidelines for specific offences developed by the Lord Chief Justice’s Sentencing Group and by guideline judgments issued after cases heard by the Court of Appeal. This collective guidance indicates, where relevant, that the judiciary should consider the age and vulnerability of the victim as an aggravating factor when determining the appropriate sentence in the individual case. Sentencing is always entirely a matter for the independent judiciary. In making these decisions, judges take a number of factors into account: the seriousness of the offence; the maximum penalty set by law; the range of available disposals; the circumstances of the offender including previous convictions; the protection of the public; the impact on the victim or their family; and any aggravating or mitigating factors in the case. The guidance in the form of sentencing guidelines and guideline judgments is published on the Judicial Studies Board website: http://www.jsbni.com/Pages/default.aspx | Achieved | Unclear | The Detail asked the DOJ what measures have been introduced and whether or not they are being implemented.
DOJ | Improve community safety by tackling anti-social behaviour | Policing and Community Safety Partnerships (PCSPs) fully operational etc | Monitor quarterly and publish annually NI Crime Survey findings etc | Increase the percentage of people who agree that police and other agencies are dealing with ASB etc | 3 | PfG Commitment achieved. Progress continues to be made on the delivery of the anti–social behaviour (ASB) commitments outlined in the Community Safety Strategy for Northern Ireland. There has been a general downward trend in the number of anti-social behaviour incidents recorded since the data series began in 2006/07. While the number of anti-social behaviour incidents fell year on year between 2006/07 and 2011/12, there was an increase of 1.8 per cent between 2011/12 and 2012/13 before levels fell again by 7.1% in 2013/14. The number of incidents then rose by 0.5% from 60,706 recorded in 2013/14 to 60,982 recorded in 2014/15; the level seen in 2014/15 is the second lowest since the data series started in 2006/07. | Progress continues to be made on the delivery of the anti – social behaviour (ASB) commitments outlined in the Community Safety Strategy for Northern Ireland. The latest findings from NI Crime Survey based on interviews conducted during the period October 1, 2014 to September 30, 2015 show that the proportion of respondents who claim that ASB has a minimal impact on their quality of life is 86.7% (PfG target an improvement percentage of people using baseline of 82.1%). The percentage of people who agree the police and other agencies are dealing with ASB and crime issues that matter in their area is 42.4% (PfG target increase to 41.4%). The percentage of people who perceive the level of ASB in their area to be high is 7.7% (PfG target reduce to 11%). PSNI statistics demonstrate that there has been a general downwards trend in the number of anti-social behaviour incidents recorded since the data series began in 2006/07 with the figure for latest twelve months to February 2016 showing the lowest level in the series. While the number of anti-social behaviour incidents fell year on year between 2006/07 and 2011/12, there was an increase of 1.8 per cent between 2011/12 and 2012/13 before levels fell again by 7.1 per cent in 2013/14. The number of incidents rose by 276 (0.5 per cent) between 2013/14 and 2014/15; however the level recorded during the latest twelve months to February 2016 (58,823) is 3.5 per cent (2,159 incidents) lower than the level recorded during 2014/15 (60,982). | Achieved | Achieved
DOJ | Improve access to Justice | Publish Departmental response to Access to Justice Review and associated Departmental Action Plan | Introduce legislation to give effect to reforms requiring primary legislation | Implementation of reforms | 3 | PfG Commitment achieved. Commencement Order for the Legal Aid and Coroners' Courts Act 2014 has been laid along with the associated subordinate legislation to allow the Legal Services Agency to take on responsibility for the delivery of legal aid from 1 April 2015. Further reforms are proceeding in line with plan. The Access to Justice Review Part II will report in summer 2015. | The Legal Services Agency assumed responsibility for the delivery of legal aid from 1 April 2015. Further reforms are on track. The Access to Justice Review Part II has been published and an Access to Justice Programme Board, involving senior representatives from DFP, DHSSPS and DSD as well as DOJ has been established to take forward agreed recommendations. | Partially achieved | Unclear | The Detail asked the DOJ how this commitment is measured. The Detail has recently reported on delays in cases in the family courts, plus a lack of legal representation for families in inquests.
DRD | Upgrade the Coleraine to Derry/Londonderry railway line |  | Complete Phase 1 etc | Phase 2 etc | 3 | PfG Commitment achieved. Phase 1 is complete. Translink’s project team has been progressing with the Phase 2 works on the Coleraine to Derry/Londonderry railway line. Signalling designers have been appointed and they have completed work on high level scheme design. Contractors have been appointed to undertake Phase 2 of the upgrade which involves full re-signalling and the addition of a passing loop at Bellarena. |  | Achieved | Achieved | Phase 2 expected to be complete by late 2016. Passing loop installed with signalling works underway.
DRD | Invest over £500m to promote sustainable modes of travel | £298 million invested | £389.5 million invested | Over £500 million invested | 3 | PfG Commitment achieved. Over £500m invested over the PfG period. |  | Achieved | Achieved | A cumulative total of £506.75 million was invested over the 4-year period up to 31 March 2015. So, looking simply at the total, it can be seen as an achieved target. However, the investment in road schemes must be questioned, so too must the impact of this expenditure as without detailed analysis there is no robust evidence that this investment has contributed to the reduction of greenhouse gases. Elsewhere the executive failed to deliver on road building pledges.
DRD | By 2015 create the conditions to facilitate at least 36% of primary school pupils and 22% of secondary school pupils to walk or cycle to school as their main mode of transport | 33% (Primary School) 21% (Secondary School) | 34% (Primary School) 21% (Secondary School) | 36% (Primary School) 22% (Secondary School) | 3 | PfG Commitment achieved. The year two delivery of the Active School Travel initiative is coming to an end with skills training being delivered to 114 primary and 12 post primary schools, involving a total school population of 45,000 pupils. The programme will create the conditions for 27% of primary and 14% of post-primary pupils to travel actively to school, building on the 27% and 13% at the outset of the project. (Totals 54% and 27%) |  | Achieved | Partially achieved | Conditions may have been created. However, according to the 2014/15 Continuous Household Survey (CHS), 30% of primary school pupils walk or cycle to school as their main mode of transport compared with 20% of post primary school pupils. In 2013/14, 31% of primary school pupils and 22% of post primary school pupils walked or cycled to school as their main mode of transport. These fall short of the annual targets for 2013/2014 and 2014/2015.
DHSSPS | Introduce a package of measures aimed at improving Safeguarding Outcomes for Children and Vulnerable Adults | Develop a Strategic Plan for Adult Safeguarding etc | Open new Sexual Assault Referral Centre at Antrim Area Hospital | Develop an updated inter-departmental Child Safeguarding Policy Framework | 3 | PfG Commitment achieved. Nine key actions are now completed and progress continues to be made against each remaining key action. The Strategic Plan (2013-2018) for Adult Safeguarding was published by the HSC Board on 14 October 2013. The joint Domestic and Sexual Violence Strategy was issued for consultation on 15 January 2014; the final strategy is nearly completed. Regulations to introduce and enforce compulsory registration with the NISCC for specified groups of social care workers came into operation in October 2013. Consultation on the draft government policy on Adult Safeguarding, including consultation on legislative proposals to support the policy closed on 31 January 2015. DHSSPS has led on the development of the updated and revised policy guidance ‘Co- operating to Safeguard Children and Young People in Northern Ireland’ with input from other government departments and their arms length bodies. The policy was launched for public consultation on 19 May 2015. Mental Capacity Legislation, to provide a range of additional safeguards for people who lack capacity to make decisions for themselves in relation to their care, treatment or personal welfare, has progressed through the Assembly. The Mental Capacity Bill was introduced on 8 June 2015, passed Second Stage on 16 June, and is now with the ad hoc joint committee for scrutiny. |  | Achieved | Achieved
DRD | Maintain a high quality of drinking water and improve compliance with waste water standards by investing £668m in water and sewerage infrastructure | Compliance with regulatory targets | Compliance with regulatory targets | Compliance with regulatory targets | 3 | PfG Commitment achieved. NI Water is on track to achieve its annual operational performance target for drinking water and wastewater compliance. |  | Achieved | Unclear | The Detail asked DRD how much of the £688m was invested over the Programme for Government timeframe but did not receive a response.
DCAL | Develop sports stadiums as agreed with the IFA, GAA and Ulster Rugby | Develop and agree programme of developments etc | Implement key milestones | Implement key milestones | 4 | UBIRFU – The Ulster Rugby Kingspan Stadium, including the education and heritage centre and community facilities, is now complete. IFA – The Windsor Park project is progressing well. Construction work commenced on site on 6 May 2014, and is continuing. UCGAA – Construction work at Casement Park is currently delayed due to the quashing of the existing planning approval on 18th December 2014. There is a strong resolve within the Ulster GAA to submit a new planning application for Casement Park. |  | Not achieved | Not achieved
DCAL | Host the World Police and Fire Games in 2013 | Develop plans and project arrangements | Host the Games |  | 4 | PfG Commitment achieved. |  | Achieved | Achieved
DETI | Support the successful hosting of the 2012 Irish Open and build on that success to secure a further international golf event | Successfully host the 2012 Irish Open Golf Championship | Secure the Irish Open for Northern Ireland in 2015 | Develop plans and project arrangements to host the Irish Open in 2015 | 4 | PfG Commitment achieved. |  | Achieved | Achieved
DSD | Deliver at least 30 Schemes to improve landscapes in public areas to promote private sector investment in towns and cities across Northern Ireland | 10 Public Realm Schemes delivered | 10 Public Realm Schemes delivered | 10 Public Realm Schemes delivered | 4 | PfG Commitment achieved. DSD continue to deliver public realm schemes across Northern Ireland. Urban Regeneration strives to make cities attractive places to live, work and invest, in order to grow our economy, create opportunities and tackle disadvantage. DSD makes use of a number of regeneration measures to achieve this purpose. One of the most important measures is public realm improvement schemes, which deliver a range of economic, social and environmental benefits. The Department continues to build on achievements last year, with 28 new schemes being completed in the 2014/2015 financial year. |  | Achieved | Partially achieved | The department failed to reach its target of 30 schemes. The Detail asked DSD for the number of schemes delivered across the PfG period as figures were only provided for one year. The department did not respond.
OFMDFM | Publish the Cohesion, Sharing and Integration Strategy to build a united community and improve community relations | Finalise strategy and agree early actions etc | Achieve early milestones in the plan etc | Achieve milestones and review performance etc | 4 | PfG Commitment achieved. T:BUC was published on 23 May 2013. The Strategy commits to the establishment of a number of thematic subgroups, two of which have been established. The Housing and Community Tensions Subgroups have met on a number of occasions. A further 3 Urban Villages have been announced bringing the number to five. Stakeholder engagement is progressing on the first two, Colin and Lower Newtownards Road. This process has commenced in the new areas. Over 150 pilot applications were submitted in December following a call for concept proposals to deliver pilot projects under the United Youth Programme. Fifty successful organisations were selected to proceed to a further development stage following which around 10 pilot schemes will be taken forward to move into delivery mode. A further call for applications for the shared education campuses resulted in six applications comprising 20 schools, these are being assessed. DCAL has completed a 12 week pilot youth sports programme. The pilot programme was launched of 5 January and finished at the end of March. The areas of Lower Falls and the Greater Village were the two Action Zones for the pilot project. The evaluation of this pilot will help to inform the overall programme. The first social housing development under the Shared Neighbourhoods Programme at Ravenhill Road has opened and a community cohesion plan is being developed to ensure that area remains a shared neighbourhood, with work continuing on a number of other sites. With regard to Summer Camps Pilot Programme 2015, OFMDFM is working in partnership with the Education Authority to deliver this Headline Action in 2015. A number of summer intervention activities and summer school/camp pilots have taken place since the summer of 2014 and further schemes were delivered until the end of March 2015. A Co-Design Team has been set up to consider an independent evaluation of these schemes and plan the design of the full pilot programme. Work is continuing with departments to take forward work in relation to the other actions and commitments arising from the strategy. |  | Achieved | Achieved | The Detail asked OFMDFM to confirm if the strategy has been reviewed in terms of its performance but did not receive an answer.
DOJ | Actively seek local agreement to reduce the number of ‘peace walls’ | Establish inter-agency collaborative approach etc | Implementation of action plans etc | Implementation of action plans etc | 4 | PfG Commitment achieved. On interfaces good progress has been achieved in ensuring that there is an appropriate level of support and engagement within relevant government departments, within key statutory agencies, and in the police and other agencies responsible for safety and security. In addition engagement through partnership programmes, such as IFI, Belfast City Council, and the NIHE, has ensured that local approaches are being developed involving community representatives and local residents. The overall number of DoJ structures has been reduced from 59 to 52. Engagement has been initiated on 40 of the DoJ's 52 structures. IFI approved funding for 8 specific community engagement projects, covering a number of the structures. Specific action plans have been developed covering 24 structures. | Ulster University provided policy papers on addressing removal of interface challenges. The Institute for Conflict Research completed three reports on issues facing certain interface communities. Seven IFI funded projects continue to assist community dialogue and develop plans to remove/alter barriers. The second Attitudes to Peace Walls Survey was published. A DOJ led cross-departmental Programme Board was established. The number of structures is now 51, reduced from 59, with parts of five other structures also removed. | Partially achieved | Partially achieved
DOJ | Reform and modernise the Prison Service | To have a new Operating Model in place etc | To have new certificates and licenses for professionalising the Service | Implement 90% of the recommendations contained in the Prison Review Action Plan within the agreed timescales | 4 | PfG Commitment achieved. The Prison Review Oversight Group has signed-off 21 of the 40 PRT recommendations as complete, and has referred an additional 16 recommendations for independent assessment. (Total 37/40, 92.5%). | With 36 of the 40 PRT recommendations signed-off by the Oversight Group, the PfG commitment to achieve 90% of the PRT recommendations has been met. The Oversight Group concluded its work by identifying five strategic themes on which the Prison Service Management Board should focus to continue the process of reform: leadership; purposeful activity; equality & diversity; fit for purpose prison estate; and partnership with Healthcare. | Achieved | Achieved | The Detail asked the DOJ if recommendations that are not signed off can be considered as having been implemented. The area of prison reform and modernisation remains highly controversial, with major criticisms around the levels of progress.
DE | Significantly progress work on the plan for the Lisanelly Shared Education campus as a key regeneration project | Develop a business case and plan etc | Secure funding and initiate the development programme | Complete procurement process and initiate first phase of construction | 4 | PfG Commitment achieved. Construction of the new Arvalee School & Resource Centre began in March 2015. Demolition of the remainder of the site began in February 2015. |  | Achieved | Achieved
DE | Establish a Ministerial advisory group to explore and bring forward recommendations to the Minister of Education to advance shared education | Establish group and produce report with recommendations |  |  | 4 | PfG Commitment achieved. |  | Achieved | Achieved
DE | Ensure all children have the opportunity to participate in shared education programmes by 2015 | Define the objectives in terms of children participating in shared education programmes | Put in place measures to achieve objectives | Achieve overall commitment objective | 4 | PfG Commitment achieved. The first call for applications to the £25m DSC Shared Education Signature Project was issued on 27 November 2014. The target is schools already involved in shared education with the aim of further embedding work in these schools. Applications for thirty one partnerships comprising 66 schools were approved, with a further eleven partnerships invited to resubmit applications. A second call for applications for partnerships commencing from September 2015 issued on 20 March with a closing date of mid-May. | The DSC Shared Education Signature Project was open for all schools to apply. Applicants who demonstrated they satisfied the required criteria were successful in receiving funding. | Achieved | Achieved
DE | Substantially increase the number of schools sharing facilities by 2015 | Define the objectives in terms of children sharing school facilities | Put in place measures to achieve objectives | Achieve overall commitment objective | 4 | PfG Commitment achieved. Progress remains on target to meet the milestone targets. High level objectives for children sharing school facilities have been defined. Baseline statistics have been established from the 2013 school omnibus survey and published in January 2014. Three projects have been approved for Business Case development. The criteria for application approval have been reviewed in advance of the second call for applications launched on 1 October 2014. The second call closed on 30 January 2015. 6 applications involving more than 20 schools were received. These are currently being assessed. | The minister expects to announce successful projects to proceed to planning from this call in June 2015. In the 2013 School Omnibus survey, 157 schools out of the 593 who responded; 28% indicated that they shared facilities; the 2015 School Omnibus survey indicated that 267 schools out of the 450 who responded; 59% shared facilities. An increase of 110 schools; 31 percentage points. The Executive’s Programme for Government set out 82 commitments to action covering some of the most strategically significant projects, programmes and policies for delivery by Departments in the last Assembly period. Alongside these commitments, outline plans for delivery of these commitments were provided in the form of annual milestones. These milestones were intended to illustrate how progress towards achievement of commitments might be made. In many cases, plans for the delivery of commitments changed over the course of the implementation of the Programme for Government, in response to changing circumstances, or to emerging evidence in relation to the most effective means of delivery, for example. For this reason, there are a number of instances where Programme for Government Commitments have been achieved, without the initial course described by the milestones being followed precisely. In addition, the Department of Education achieved six of its eight commitments, as well as delivery within the Assembly mandate of an alternative to the commitment to the make the Education and Skills Authority operational (i.e. the Education Authority). | Achieved | Unclear | The Detail asked the department how many schools were sharing facilities by 2015 compared to 2011. The department responded with the results of two surveys. There are more than 593 schools in Northern Ireland, suggesting that many did not feature in the survey findings. The results were therefore based on a partial survey.
DFP | Include Social Clauses in public procurement contracts for supplies, services and construction | Develop a Procurement Guidance Note on social clauses etc | Monitor implementation | Monitor implementation | 5 | PfG Commitment achieved. Central Procurement Directorate continues to advise Departments on the inclusion of social clauses in government contracts and to record data for the end-year report to the Procurement Board. |  | Achieved | Not achieved | The DFP's Construction Procurement Policy Framework, published in December 2015, suggests social clauses are not yet commonplace in all contracts. It states: "Following a review of social clauses in Northern Ireland, the Procurement Board agreed construction works threshold values above which recruitment and training opportunities should normally be applied: £2 million for building contracts and £4 million for civil engineering contracts. For other contracts, Departments should consider how social considerations can be included with reference to PGN 01/13 -integrating social considerations into contracts. The Procurement Board also agreed to the establishment of a cross departmental Social Clause Reference Group to inform future policy and support implementation of social considerations." (See: https://www.dfpni.gov.uk/sites/default/files/publications/dfp/PGN-06-2010-18-December-2015.PDF)
DOE | Establish the new 11 council model for Local Government by 2015 | Progress legislation and programme structure etc | Arrangements in place for the shadow Councils etc | Arrangements in place for the transfer of powers to councils etc | 5 | PfG Commitment achieved. Powers and responsibilities were transferred to the eleven new councils at midnight on 31st March 2015. The new councils are now fully operational. |  | Achieved | Achieved | This followed major delays in delivery of the reform predating the PfG. There are ongoing concerns over elements of how the new councils will operate.
DE | Make the Education and Skills Authority operational in 2013 | Bring forward legislation etc | Take forward structural, financial and other actions etc | Single Education Authority established and fully functional | 5 | Commitment withdrawn by the Executive. A new Education Authority has been established. |  | Withdrawn | Not achieved
OFMDFM | Agree any changes to post-2015 structures of Government in 2012 | Consider relevant reports, engage with UK Government etc | Introduce any necessary Assembly legislation etc | Complete administrative and legal preparations for post-2015 structural changes | 5 | PfG Commitment achieved. Further to the commitment in the Stormont House Agreement of December 2014 on a reduction in the number of Departments, the Executive agreed in January and February 2015 the redistribution of departmental functions, the names of the future Departments and the timescale for passage of a Departments Bill. The First Minister announced these decisions in an oral statement to the Assembly on 2 March 2015. |  | Achieved | Achieved
DFP | Improve online access to government services | Develop plans and specific targets etc | Monitor early progress etc | Review level of access of online services etc | 5 | PfG Commitment achieved. The digitally transformed services launched have been well received by citizens and uptake has exceeded original expectations with over 2 million transactions completed during the 2014/15 year. Work is continuing to progress the long list of services Digital Transformation Programme. |  | Achieved | Achieved | The Detail asked DFP for further information on what the 2 million figure refers to, but did not receive an answer.
DHSSPS | Improve patient and client outcomes and access to new treatments and services | Enhance access to life-enhancing drugs etc | Improve long-term outcomes etc | Expand cardiac catheterisation capacity etc | 5 | PfG Commitment achieved. Since September 2014 the Primary Percutaneous Coronary Intervention (PPCI) service for patients suffering the most severe form of heart attack is provided to the entire Northern Ireland population from two centres in the Royal Victoria Hospital and Altnagelvin Hospital. |  | Achieved | Unclear | The department's quarterly update failed to provide any evidence that the first two milestones were achieved. The Detail asked the department for information on other new treatments and services as the executive's latest update only refers to heart attack treatment, but did not receive a response.
DHSSPS | Reconfigure, reform and modernise the delivery of Health and Social Care services to improve the quality of patient care | Development of a clear implementation and Population plan etc | Reduce by 2013/14 the number of days patients stay in acute hospitals unnecessarily etc | Secure a shift in from hospital based services to community based services etc | 5 | PfG Commitment achieved. A Strategic Implementation Plan for HSCB led service changes in response to Transforming Your Care was delivered in October 2013. The target reduction in the number of days patients stay in acute hospitals unnecessarily (excess bed days) has been achieved. The transition to the new model of care envisaged in Transforming Your Care in a safe and sustainable manner is a long term process and one which is influenced by our financial circumstances. Steady progress has been made including the implementation of 17 Integrated Care Partnerships across Northern Ireland; resettlement of mental health and learning disability clients in the community; provision of reablement services for older people; development of acute care at home services; and development of new NI Ambulance service pathways to support reduced Accident and Emergency attendances and better patient experience. |  | Achieved | Achieved | This remains a controversial area with many elements of reform still in progress.
DSD | By the end of 2014/15, to have implemented new structures to support the improved delivery of housing services to the citizens of Northern Ireland | To develop and consult on service delivery structures etc | Deliver year 1 of implementation programme | Implement new structures | 5 | The Social Housing Reform Programme continues with a revised objective to progress Social Housing Reform, making recommendations on the preferred options. |  | Not achieved | Not achieved | The Detail asked DSD if the new structures have been implemented but the department did not respond.
DFP | Further reduce the levels of sickness absence across the NICS | Reduce the average annual days sick absence per employee to 9.5 days | Reduce the average annual days sick absence per employee to 9.0 days | Reduce the average annual days sick absence per employee to 8.5 days | 5 | NISRA reported on 16 October 2014 that the NICS sickness absence levels for 2013/14 was 10.1 days (average days lost per staff year), down from 10.6 days in the previous year but short of the annual target of 9.0 days. However based on the targets and estimates figures produced by NISRA (February 2015) it is anticipated that the 2014/15 target of 8.5 days lost per staff year will not be met, 10.8 days is anticipated. As part of the 2014/15 work programme to address the progress towards targets Permanent Secretaries agreed a NICS-wide recovery strategy which is currently being considered by the Finance and Personnel Minister. In addition a range of actions are being progressed through the NICS People Strategy 2013/2016 and associated Annual People Plan 2014-2015. |  | Not achieved | Not achieved